## Лист1
Facilities, Measures, and Their Implementation Status in 2013
| Facilities and Measures | Implementation Status
Copper Factory
| ● Construction of the cement copper pelletising apparatus at the slag yard of the Copper Factory. | ● Working meetings were held with representatives of the contractor company to address the technical issues of contract implementation.
| ● Reconstruction of the second production line producing elemental sulphur. | ● A large number of design and exploration works were conducted.
● Pilot and semi-industrial tests were conducted in the USA and the Czech Republic. Positive results were obtained.
| ● Implementation of the technology of continuous conversion, including utilisation of sulphur dioxide. | ● Work on the topic “Feasibility Study of an Optimal Variant of Copper Nickel-Containing Matte Conversion at the Copper Factory” completed.
● Research and development activities, including the development and adoption of technological regulations, completed.
● Work continues in the development of a technology for processing fluid nickel slags obtained in the course of continuous conversion at the Copper Factory within the framework of the pyrometallurgical production at the Nadezhda Metal Plant.
Nadezhda Metal Plant
● Reconstruction of the sulphur production workshop No. 2 and construction of the warehouse for a long-term storage of sulphur.
● Analogous to the project “Reconstruction of the Second Production Line for Production of Elemental Sulphur” at the Copper Factory.
| ● Conducting step-by-step reconstruction and modernisation of the pyrometallurgical production at the Nadezhda Metal Plant accompanied by a simultaneous modernisation of the systems for purification of waste gases from dust accompanied by replacement of electrical filters. | ● Pre-commissioning activities.
| ● A new high-powered depletion furnace. | ● Reconstruction of the Gas Purification Apparatus GPA-2 accompanied by replacement of cyclones with a bag filter––a device characterised by a high degree of purification of waste gases.
| ● Reconstruction of dust collection site including installation of a new electrostatic precipitator produced by BHA for purification of waste gases. | ● Procurement of equipment and equipment accessories.
Cement plant
| ● Reconstruction of shaft gas furnaces and purification systems | ● Industrial exploitation of the filter carried out.
● Raising efficiency of the electrostatic precipitator of a grate cooler by installing a bag filter with pulse-jet filter elements therein.
Kola MMC
● Modernisation of equipment at Kola MMC contributed to a reduction in the amounts of gases ingressing into the workspace, improvement of working conditions, increase in the degree of utilisation of sulphurous gases producing sulphuric acid, and a significant reduction (to the lowest possible levels) of emissions of sulphur dioxide, dust, and other contaminants.
Nickel
● Sealing of metallurgical equipment at the melting shop.
● Computerised system for management of flow of gases emerging from converters.
● Replacement of obsolete equipment at the sulphuric acid division of the refinery.
Zapolarny
● Intoduction of a new technology of cold briquetting of the concentrate replacing roasting.
Murmansk Transport Branch
● Conducting regular preventive inspections and repairs of marine and coastal transport.
● Purchase of marine fuel, the quality of which is confirmed by an independent laboratory.